## CIAT
CENTRE NAME: |  | CIAT
AUDITORS: |  | Janny van Beem (QMS and Standards), Simon Linington (Standards)
AUDIT SCOPE: |  | Conservation--documentation audit
AUDIT DATE: |  | 26 April 2018 - 31 of August 2018
REPORT DATE: |  | 20 of July, 2018
AUDIT FINDINGS | [7 empty] | POST-AUDIT RESPONSE |  | Clearance Round 1 (Y/N) | COMMENTS | Clearance Round 2 (Y/N/NA) | COMMENTS | CLEARANCE DATE
Finding No. | Location/ Section | Clause and Source | Description of the finding | Proposed Improvement | Mandatory or Recommendation (M/R) | Evidence required (Y/N) | Evidence due date | Actions taken to address finding | Evidence provided (such as links, documents)
CIAT-2018-CONS-1 | Policy | Clause 3.3.1 QMS: Audit Guide and Clause List v1.6 | The QMS Audit Guide and Clause List states that "the genebank shall have policies regarding germplasm in its collections including criteria for acquisition, introduction into long-term storage, medium-term storage and temporary holdings, inactivation, reactivation, archiving, duplicates, distribution, safety duplication and availability. " The Conservation SOP does not adequately describe curation policies. | Submit the genebank's curation policies as a Related Document. The conservation policies should describe criteria for the introduction of accessions into long-term, medium-term and temporary storage (e.g., mandate, legal status, health status, quantity and viability/vigour thresholds, the intervals at which accessions are tested for viability/vigour, the actions when viability/vigour and inventory fall below thresholds, "de-materialization" (e.g., in the event of loss of an MLS accession), and the steps taken when duplicate accessions are identified). | M | Y | 2018-08-03 | We will answer finding "CIAT-2018-CONS-1” once the current work of the GB Platform Working Group on Accession Management has been concluded because our conservation policies will need to be modified to be fully aligned with the results of this working group. This is of particular importance in relation to the implementation of the Tropical Forages Strategy. |  | Y | Genebanks currently have some operational, curation and QMS policies within SOPs. Members of the Policy Module are working towards creating a collective policy document which will be shared among genebank managers by the end of 2018 . | NA | Finding cleared in Round 1 | 2018-09-28
CIAT-2018-CONS-2 | Introduction | QMS | The ORT report for 2017 states that the genebank collection is composed of 68,339 accessions. The GENESYS Institution Report and CIAT's genebank website state that the genebank conserves 67,770 accessions. Numbers reported yearly in various sites (such as the genebank's website, GENESYS, ORT, Genebank Platform and SOPs) should be identical. | Confirm that the number of accessions and species reported yearly in the genebank's website, GENESYS, the Crop Trust Online Reporting Tool (ORT), the Genebank Platform and the Conservation SOP are exactly the same. Ensure that the genebank has a protocol in place to periodically update information across public and private websites. | M | Y | 2018-08-03 | We just checked the information contained in the ORT 2017 (# of accession in Beans, Cassava and Forages) and found the numbers corresponding to 67.770, not 68.339 as indicated in the finding - so we do not know where the 68.339 comes from. We placed an initial sentence indicating the total number of accession conserved in the genebank. We clarify the periodical update of information here in the introduction. | ORT 2017, revised on 25.07.2018 .Page 3 | Y | Introduction section now includes a protocol on how various sites are updated, including GENESYS. | NA | Finding cleared in Round 1 | 2018-09-28
CIAT-2018-CONS-3 | Procedure | Clause 4.4.3, FAO. 2014. Genebank Standards for PGRFA | The FAO Genebank Standards state that "at least 50 seeds of the original and subsequent most-original sample shall be archived in long-term storage for reference purposes." The SOP does not describe activities related to preparation and storage of reference or voucher samples of seed. | Include steps in the Conservation SOP describing how many seeds are prepared in the voucher sample (seed file), where they are stored and how they are used in the authentication or identity verification process. | M | Y | 2018-08-03 | We adjusted the paragraphs in page 36 to clarify the voucher sample procedure and also in the packing section. How these voucher samples are used for authentication is explained in page 26, line 6.25 | Lines 6.36.2, 6.36.3 and 6.77.4. | Y | Voucher sample preparation and storage is explained on page 36 and authentication protocol explained on page 26-27. | NA | Finding cleared in Round 1 | 2018-09-28
CIAT-2018-CONS-4 | Procedure | Text, pages 10 and 37, FAO. 2014. Genebank Standards for PGRFA | The FAO standards state that "genebanks shall ensure that the genetic composition of the originally-collected sample is maintained". Seed processing methods in the SOP describe how samples are passed through sieves and then processed through homogenizer and shakers in order to homogenize seed lots. It is unclear how the genebank handles seed samples with inherent variability and heterogeneity in seed size and shape (e.g., wild species and landraces). | Explain how samples that are naturally variable and heterogeneous for various characteristics are preserved as such. | M | Y | 2018-08-03 | When an accession is inherently variable, we classify the separate morphologies in different bags or jars, and then discuss among responsible staff about pertinence of maintaining them as independent accessions - procedure mentioned in lines 6.24; 6.25 y 6.26 pages 24-26. | Lines 6.24; 6.25 y 6.26 pages 24-26. | Y | Protocol for handling heterogeneous accessions is described in 6.25.4 and consists of de-bulking the accessions into sub-samples and collectively making a decision on a case-by-case basis. | NA | Finding cleared in Round 1 | 2018-09-28
CIAT-2018-CONS-5 | Procedure | Text, page 33, FAO. 2014. Genebank Standards for PGRFA | The FAO standards state that "every effort shall be made to germinate all viable seeds using optimum conditions and appropriate dormancy-breaking treatments where needed". The SOP does not adequately describe the dormancy-breaking treatments used prior to viability testing. | Add text in the SOP that describes the genebank's dormancy-breaking treatments for the species conserved. | M | Y | 2018-08-03 | We included some clarifications to ease the understanding of the different methodologies that we are applying at the moment in the viability lab for breaking seed dormancy prior to viability evaluation. Also within the SQM project with are evaluating other methodologies for breaking dormancy (proactive management) | Lines 6.62.; 6.64.2.11; 6.64.2.11.1 6.64.2.11.2; 6.64.2.13.1; page 110 proactive management. | Y | Scarification, light, temperature and gibberellic acid have been added as ways to break seed dormancy. | NA | Finding cleared in Round 1 | 2018-09-28
CIAT-2018-CONS-6 | Procedure | QMS | A comprehensive Conservation SOP describes sample preparation for storage, testing and safety duplication. For ease in viewing the information at a glance, sample preparation for the following activities could be consolidated in a table: LTS, MTS, phytosanitary testing, viability testing, distribution, safety duplication, regeneration and the 50-seed voucher sample. | A template was provided along with this Finding Report as an example of a consolidated table (see second sheet-tab below). Tailor the table to suit your needs when consolidating your sample preparation activities. Include the table in the SOP. | M | Y | 2018-08-03 | We prepared this table, and included it at the end as a review of the numbers of seeds per objective. For regeneration we indicated that tables 12 and 13 must be checked, as the numbers of seeds depends on the species. | Lines 6.96 y 6.97 | Y | Annex 3 contains a summary of processes, frequency and seed numbers. Additional figures are mentioned in the packing section (Step 6.77, Tables 7 and 8). | NA | Finding cleared in Round 1 | 2018-09-28
CIAT-2018-CONS-7 | Procedure | Text, p 27, FAO. 2014. Genebank Standards for PGRFA | The FAO Genebank Standards state that "after drying, all seed samples for long-term storage shall be packaged in a barcode-labelled, vacuum-sealed trilaminate aluminium foil packet." It is unclear how genebank staff ensure that foil packets are properly vacuum-sealed. | Describe the method by which the foil bag sealer is tested to ensure satisfactory sealing. | M | Y | 2018-08-03 | We include two additional points indicating the order of sealing the foil bags, starting at the lower end, packing, and then sealing the upper end, turning the bag upside down, and corresponding verification of vacuum. | Lines 6.78.1. and 6.78.2 | Y | Steps 6.78.1 and 2 adequately describe how proper sealing of aluminium bags is confirmed and re-checked. | NA | Finding cleared in Round 1 | 2018-09-28
CIAT-2018-CONS-8 | Materials and Equipment | Clause 4.7.2, FAO. 2014. Genebank Standards for PGRFA Genebanks CRP Barcoding Initiative 2016 | The FAO Genebank Standards state that "All data and information generated in the genebank relating to all aspects of conservation and use of the material should be recorded in a suitably designed database." Although improvements have been made regarding centralized databases and barcoding, it appears that there are areas and procedures where data is not captured in databases and barcodes are not used for data retrieval and capture. | State if the genebank captures data and information related to all processes of conservation and use in a central database and makes use of barcoding for data retrieval and capture. Submit a brief update including: 1) a list of areas and procedures in which data is retrieved and captured from a central database and barcodes are used for data retrieval and capture, 2) a list of areas and procedures in which data is not yet directly integrated into a central database and barcodes are not utilized and, 3) the plan to put into operation a central database and implement barcoding in areas, procedures and locations where they are not currently used. | M | Y | 2018-08-03 | We included a statement indicating the processes where we are capturing information in digital form (real-time database use, including a list of the processes per crop, and also the implementation plan for the process lacking this link (seeds reception for beans). | Pages 13-14 | Y | Processes that have been barcoded are listed in pages 13-14. Processes still pending to be barcoded are also listed and will be addressed by the end of 2018. | NA | Finding cleared in Round 1 | 2018-09-28
CIAT-2018-CONS-9 | Materials and Equipment | QMS-Equipment | The Materials and Equipment section does not state the specifications for barcode labels and ribbons that would withstand the extreme temperature, moisture and light conditions in genebank operations. | Specify in the Materials and Equipment section the type of printers, ribbons (ink) and labels used for barcoding in seed processing, drying, MTS and LTS that are explicitly manufactured to withstand extreme temperatures, moisture and light. | M | Y | 2018-08-03 | We added lines with references for printers, ribbons and labels. | Pages 9, 10 and 12 | Y | Manufacturer and model/specifications for printer labels and ribbons has been added in Section 5 of the SOP | NA | Finding cleared in Round 1 | 2018-09-28
CIAT-2018-CONS-10 | Infrastructure and Work Environment | Text, p 27, FAO. 2014. Genebank Standards for PGRFA | The FAO Genebank Standards state that "the genebank shall maintain records of storage temperature deviations and periods when seed accessions are removed from the storage environment " The SOP describes the temperature and relative humidity in several chambers. It is unclear how deviations in temperature and humidity are monitored and the mechanism by which deviations in these parameters are immediately corrected. Additionally, it is unclear how frequently the alarms related to monitoring conditions in the rooms are calibrated and tested. | Review the process by which temperature and relative humidity are monitored and corrected. Add text in the Infrastructure and Work environment section describing how deviations in temperature and relative humidity are immediately detected and corrected. For temperature and relative humidity alarms, submit the schedule for calibration and testing. | M | Y | 2018-08-03 | We introduced a page with the relevant information regarding control of conditions (temperature, humidity), equipment, and contingency procedures in case of malfunction. The frequency of monitoring of these conditions is indicated, as well as the calibration/maintenance of equipment. | Pages 103, 104 and 105 | Y | Text in Section 9 adequately describes the monitoring of temperature and RH on a daily basis; actions and contingency plans when deviations are detected or for maintenance purposes are also described. | NA | Finding cleared in Round 1 | 2018-09-28
CIAT-2018-CONS-11 | Infrastructure and work environment | QMS | The "Infrastructure and Work Environment" section describes area specifications, monitoring of temperature and relative humidity and specific protocols and alarms that safeguard staff and collections. The SOP does not describe the way in which the Center responds to significant threats to the collections such as fire or flooding. | In a Related Document, briefly describe the genebanks 24-hour emergency plan in the event of a significant threat to the collections such as fire or flooding. Include the following: 1) number and type of alarms and emergency equipment currently in place at the genebank and the frequency with which fire alarms are tested, 2) the mechanism by which the alarms are detected and handled (e.g., the fire alarm triggers an audible siren and sends an electronic notification to maintenance crew, genebank manager and key genebank staff), 3) the Centre's list of "First Responders " trained to address the hazards during the day, night or weekends, 4) the frequency with which the 24-hour emergency response is tested. | M | Y | 2018-08-03 | We added a description of the emergency plan currently in place, and a proposal for improvement of it in the near future. Additionally, we make reference (related documents) to CIAT's institutional emergency plan. | Pages 100, 105-109 | Y | Number and types of alarms in the genebank have been specified. The related document "Plan de prevencion, preparcion y respuesta ante emergencias" describes the Centers 24-hour response to hazardous situations. | NA | Finding cleared in Round 1 | 2018-09-28

## Summary Table-Seed Prep
Summary Table for Sample Preparation
CROP:
Sample preparation for: | Number of seed prepared | Seed source/ provenance | Packing material | Pack size | Number of packs prepared | Storage conditions (if applicable) | Comments
LTS
MTS
Temporary storage
Phytosanitary testing
Viability testing
Distribution
Safety Duplication
Regeneration
Voucher/ Reference sample | 50 | original or subsequent most-original seed sample | plastic bag | 60 x 60 mm | 1 | LTS (-18oC)
Etc